## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Autonetics and Administration for IT Laboratories |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P. Shah Information Of Technology
PROJECT GUIDE |  | Dr. Sameer Nanivadekar |  |  |  |  | DATE | [6 empty] | 2020-04-09
PROJECT CO-GUIDE |  | Prof. Vishal Badgujar
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Uddhabendra,Karthikeyan,Atharv | 2019-07-10 | 2019-07-26 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Research paper finalization | Uddhabendra,Karthikeyan,Atharv | 2019-07-10 | 2019-07-26 | 3 | 100% | bar: WEEK 2 W
1.2 | Project Title | Uddhabendra,Karthikeyan,Atharv | 2019-07-10 | 2019-07-26 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Atharv | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Uddhabendra,Karthikeyan,Atharv | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Karthikeyan | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Uddhabendra | 2018-03-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 F
1.7 | Scope | Karthikeyan | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Uddhabendra,Atharv | 2019-08-23 | 2019-08-30 | 1 | 80% | bar: WEEK 3 F
1.9 | Benefits for environment | Atharv | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | Karthikeyan | 2019-08-23 | 2019-08-30 | 1 | 80% | bar: WEEK 3 F
1.11 | Applications | Uddhabendra | 2019-08-23 | 2019-08-30 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Proposed System | Karthikeyan,Uddhabendra | 2019-09-19 | 2019-09-27 | 1 | 70% | bar: WEEK 4 M to WEEK 4 F
2.2 | Design(Flow Of Modules) | Uddhabendra,Karthikeyan,Atharv | 2019-09-19 | 2019-09-27 | 1 | 70% | bar: WEEK 4 T to WEEK 4 F
2.3 | Activity Diagram | Uddhabendra,Atharv | 2019-09-19 | 2019-09-27 | 1 | 50% | bar: WEEK 4 W to WEEK 4 F
2.4 | Use Case Diagram | Atharv,Karthikeyan | 2019-09-19 | 2019-09-27 | 1 | 50% | bar: WEEK 4 R to WEEK 4 F
2.5 | Description Of Use Case | Karthikeyan,Uddhabendra | 2019-09-19 | 2019-09-27 | 1 | 30% | bar: WEEK 4 F
2.6 | Modules |  | 2019-09-19 | 2019-09-27 | 1 | bar: WEEK 4 F
2.6.1 | Module-1 | Atharv,Karthikeyan,Uddhabendra | 2019-09-19 | 2019-09-27 | 1 | 75% | bar: WEEK 4 F
2.6.2 | Module-2 | Atharv | 2019-09-19 | 2019-09-27 | 1 | 75% | bar: WEEK 4 F
2.6.3 | Module-3 | Karthikeyan | 2019-09-19 | 2019-09-27 | 1 | 85% | bar: WEEK 4 F
2.6.4 | Module-4 | Uddhabendra | 2019-09-19 | 2019-09-27 | 1 | 85% | bar: WEEK 4 F
2.7 | Preparation Of Report | Atharv | 2019-09-19 | 2019-09-27 | 1 | 85% | bar: WEEK 4 F
3 | Project Implementation
3.1 | Module-1 | Atharv,Karthikeyan,Uddhabendra | 2020-02-04 | 2020-02-04 | 0 | 60%
3.2 | Module-2 | Atharv | 2020-02-05 | 2020-02-05 | 0 | 65% | bar: WEEK 5 T to WEEK 5 F
3.3 | Module-3 | Karthikeyan | 2020-02-11 | 2020-02-12 | 0 | 55% | bar: WEEK 5 T to WEEK 5 F
3.4 | Module-4 | Uddhabendra | 2020-02-25 | 2020-02-26 | 0 | 58% | bar: WEEK 5 W to WEEK 5 F
4 | Testing
4.1 | Design of Test Cases | Karthikeyan,Atharv | 2020-01-26 | 2020-02-02 | 3 | 40% | bar: WEEK 6 M to WEEK 6 F
4.2 | Installing Ansible | Atharv,Karthikeyan,Uddhabendra | 2020-01-27 | 2020-02-03 | 1 | 45% | bar: WEEK 6 T to WEEK 7 M
4.3 | Creating a Sample Playbook | Atharv,Karthikeyan,Uddhabendra | 2020-02-04 | 2020-02-10 | 1 | 45% | bar: WEEK 6 W to WEEK 7 T
4.4 | Testing Playbooks | Uddhabendra,Karthikeyan,Atharv | 2020-02-11 | 2020-02-17 | 1 | 50% | bar: WEEK 6 R to WEEK 7 W
4.5 | Implemented it using ansible | Uddhabendra,Karthikeyan,Atharv | 2020-02-18 | 2020-02-24 | 1 | 50% | bar: WEEK 7 T to WEEK 8 M
4.6 | Started working on various OS | Karthikeyan, Uddhabendra | 2020-02-25 | 2020-03-02 | 1 | 50% | bar: WEEK 7 W to WEEK 8 T
4.7 | Configured the ansible for various OS | Karthikeyan,Uddhabendra | 2020-03-03 | 2020-03-09 | 1 | 60% | bar: WEEK 7 R to WEEK 8 W
4.8 | Created various playbooks according to the requirment of various labs | Atharv | 2020-03-10 | 2020-03-16 | 1 | 60% | bar: WEEK 8 W
4.9 | Started Developing student lab utilization manual | Karthikeyan | 2020-03-17 | 2020-03-23 | 1 | 60% | bar: WEEK 8 W to WEEK 9 T
4.1 | Gathered information of all labs | Atharv | 2020-03-24 | 2020-03-30 | 1 | 60% | bar: WEEK 8 R
4.11 | Worked on the frontend of website | Karthikeyan | 2020-03-31 | 2020-04-06 | 1 | 70% | bar: WEEK 8 R
4.12 | Worked on the CSS of website | Karthikeyan, Uddhabendra | 2020-04-07 | 2020-04-13 | 1 | 70% | bar: WEEK 8 R to WEEK 9 W
4.13 | Worked on the backend of website | Karthikeyan | 2020-04-14 | 2020-04-20 | 1 | 70% | bar: WEEK 8 F to WEEK 9 R
4.14 | Worked on the Ansible GUI | Karthikeyan,Uddhabendra | 2020-04-21 | 2020-04-27 | 1 | 70% | bar: WEEK 9 M to WEEK 10 M
4.15 | Worked on the Inventory File | Atharv,Uddhabendra | 2020-04-21 | 2020-04-27 | 1 | 70% | bar: WEEK 9 T to WEEK 10 W
4.16 | Worked on the ssh Keys | Karthikeyan | 2020-04-28 | 2020-05-04 | 1 | 80% | bar: WEEK 9 W to WEEK 10 R
4.17 | Worked on creating multiple users with Different access permisions | Atharv,Karthikeyan,Uddhabendra | 2020-05-05 | 2020-05-11 | 1 | 80% | bar: WEEK 9 R to WEEK 10 F
4.18 | Working on the playbook running on Windows | Atharv,Karthikeyan, Uddhabendra | 2020-05-12 | 2020-05-18 | 1 | 80% | bar: WEEK 9 F to WEEK 11 M
4.19 | Worked on the implementation of Semaphore | Karthikeyan | 2020-05-19 | 2020-05-25 | 1 | 80% | bar: WEEK 10 M to WEEK 11 T
4.2 | Working on fetching the mac address and ip address at once in a single file | Uddhabendra,Karthikeyan,Atharv | 2020-04-21 | 2020-04-27 | 1 | 80% | bar: WEEK 10 R to WEEK 11 W
5 | Results and Analysis
5.1 | Analysis Of Results | Karthikeyan | 2020-02-25 | 2020-02-26 | 1 | 70% | bar: WEEK 11 R to WEEK 12 W
5.2 | Graphical Representation | Uddhabendra | 2020-03-24 | 2020-03-26 | 1 | 60% | bar: WEEK 11 F to WEEK 12 R
5.3 | Report Preparation | Atharv | 2020-03-25 | 2020-03-27 | 1 | 80%